## Sheet1
Jyothy Institute Of Technology Project Work Breakdown Structure
Project Title : Emerging Societal Problems Organised and Immediately Resolved – Version 3
Date | Hamsa J |  | Sanjana S.A. |  | V.Anagha Tiru |  | Sahana A
2016-08-07 | Installing Ionic Framework |  | Installing Ionic Frame work |  | Installing Ionic Framework
2016-09-07
2016-11-07
2016-12-07
13/7/2016 | Installing Android Studio
14/7/2016 | Building a basic blank app using Ionic Framework
15/7/2016 | Building a basic blank app using Ionic Framework... |  | Building a Tabs app using Ionic Framework |  | Building a Side menu app using Ionic Framework
16/7/2016 | Building a basic blank app using Ionic Framework... |  | Building a Tabs app using Ionic Framework... |  | Building a Side menu app using Ionic Framework...
18/7/2016 | Building a basic blank app using Ionic Framework... |  | Building a Tabs app using Ionic Framework... |  | Building a Side menu app using Ionic Framework...
19/7/2016 | Building a basic blank app using Ionic Framework... |  | Building a Tabs app using Ionic Framework... |  | Building a Side menu app using Ionic Framework...
20/7/2016 | Building a basic blank app using Ionic Framework... |  | Building a Tabs app using Ionic Framework... |  | Building a Side menu app using Ionic Framework...
21/7/2016 | Building a basic blank app using Ionic Framework... |  | Building a Tabs app using Ionic Framework... |  | Building a Side menu app using Ionic Framework...
22/7/2016 | Building a basic blank app using Ionic Framework... |  | Building a Tabs app using Ionic Framework... |  | Building a Side menu app using Ionic Framework...
23/7/2016 | Building an app using Android Studio |  | Building a Tabs app using Ionic Framework... |  | Building a Side menu app using Ionic Framework...
25/7/2016 | Building an app using Android Studio... |  | Installing BBMP Sahaya App |  | Installing BBMP Sahaya App
26/7/2016 | Building an app using Android Studio... |  | Making a list of 4th row complaint categories |  | Making a list of 3rd row complaint categories
28/7/2016 | Building an app using Android Studio... |  | Making a list of 4th row complaint categories... |  | Making a list of 3rd row complaint categories...
29/7/2016 | Building an app using Android Studio... |  | Making a list of 4th row complaint categories... |  | Making a list of 3rd row complaint categories...
30/7/2016 | Installing BBMP Sahaya App |  | Registering 4 complaints in BBMP app and know its process of working |  | Registering 4 complaints in BBMP app and know its process of working
2016-01-08 | Making a list of 2nd row complaint categories |  | Registering 5 complaints in BBMP app |  | Registering 5 complaints in BBMP app
2016-02-08 | .. |  | Registering 5 complaints in BBMP app |  | Registering 5 complaints in BBMP app
2016-03-08 | Registering 5 complaints in BBMP app |  | Make a list of bugs and errors in the BBMP Sahaya App |  | Make a list of errors in the BBMP Sahaya App
2016-05-08 | Registering 5 complaints in BBMP app |  | Make a list of bugs and errors in the BBMP Sahaya App... |  | Make a list of errors in the BBMP Sahaya App...
2016-06-08 | Make a list of bugs in the BBMP Sahaya App |  | Make a list of bugs and errors in the BBMP Sahaya App... |  | Make a list of errors in the BBMP Sahaya App...
2016-08-08 | Make a list of bugs in the BBMP Sahaya App... |  | Make a list of bugs and errors in the BBMP Sahaya App... |  | Make a list of errors in the BBMP Sahaya App...
2016-09-08 | Make a list of bugs in the BBMP Sahaya App... |  | Make a list of bugs and errors in the BBMP Sahaya App... |  | Make a list of errors in the BBMP Sahaya App...
2016-10-08 | Make a list of bugs in the BBMP Sahaya App... |  | Make a list of bugs and errors in the BBMP Sahaya App... |  | Make a list of errors in the BBMP Sahaya App... |  | Installing BBMP Sahaya App
2016-11-08 | Make a list of bugs in the BBMP Sahaya App... |  | Make a list of bugs and errors in the BBMP Sahaya App... |  | Make a list of errors in the BBMP Sahaya App... |  | Making a list of 1st row complaint categories
2016-12-08 | Make a list of bugs in the BBMP Sahaya App... |  | Make a list of bugs and errors in the BBMP Sahaya App... |  | Make a list of errors in the BBMP Sahaya App... |  | Making a list of 1st row complaint categories...
2016-10-09 | Installing Corona Sdk |  | Installing Corona Sdk |  | Installing Corona Sdk |  | Installing Corona Sdk
2016-11-09 | Working on creating various scenes -Corona Sdk |  | Working on Events and Listeners- Corona Sdk |  | Working on Graphics-Corona Sdk |  | Working on Physics-Corona Sdk
2016-12-09 | Working on creating various scenes -Corona Sdk... |  | Working on Events and Listeners- Corona Sdk... |  | Working on Graphics-Corona Sdk... |  | Working on Physics-Corona Sdk...
13/9/2016 | Working on creating various scenes -Corona Sdk... |  | Working on Events and Listeners- Corona Sdk... |  | Working on Graphics-Corona Sdk... |  | Working on Physics-Corona Sdk...
14/9/2016 | Working on creating various scenes -Corona Sdk... |  | Working on Events and Listeners- Corona Sdk... |  | Working on Graphics-Corona Sdk... |  | Working on Physics-Corona Sdk...
15/9/2016 | Building Ilearn Science app using Corona Sdk |  | Building Ilearn Science app using Corona Sdk |  | Building Let's Paint app using Corona Sdk |  | Building Let's Paint app using Corona Sdk
16/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
18/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
20/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
21/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
22/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
22/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
23/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
24/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
25/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
26/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
27/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
28/9/2016 | Building Ilearn Science app using Corona Sdk... |  | Building Ilearn Science app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk... |  | Building Let's Paint app using Corona Sdk...
2016-01-10 | SRS Specification- External Resource Requirements |  | Work Breakdown Structure |  | SRS Specification- Description |  | SRS Specification- Functional Requirements
2016-02-10 | SRS Specification- External Resource Requirements... |  | Work Breakdown Structure... |  | SRS Specification- Design Constraints |  | SRS Specification- Functional Requirements...
2016-03-10 |  |  | Work Breakdown Structure... |  | SRS Editing |  | SRS Specification- Functional Requirements...
2016-04-10 |  |  |  |  | SRS Editing...
2016-09-10 |  |  | SRS Editing
17/10/2016 |  |  |  |  | Uploading files in github |  | Abstract
21/10/2016 | Work Breakdown structure in Agile Methodology format |  | SRS- Adding Non-functional requirements
2016-10-22 | Learning Lua- Scenes and Events |  | Learning Lua- Database Management and php |  | Learning Lua- Widgets,GPS,Maps |  | Overview of the app's design
2016-10-23 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-10-24 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-10-25 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-10-26 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-10-27 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-10-28 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-10-29 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-10-30 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-10-31 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-11-01 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-11-02 | Learning Lua- Scenes and Events... |  | Learning Lua- Database Management and php... |  | Learning Lua- Widgets,GPS,Maps... |  | Overview of the app's design...
2016-11-07 | Internals-Lab | Internals-Lab | Internals-Lab | Internals-Lab | Internals-Lab | Internals-Lab | Internals-Lab
2016-11-08
2016-11-09
2016-11-10
2016-11-11
2016-11-12
2016-11-13 | Internals-Theory |  | Internals-Theory |  | Internals-Theory |  | Internals-Theory
2016-11-14
2016-11-15
2016-11-16
2016-11-17
2016-11-18
2016-11-19
2016-11-20
2016-11-21 | Design 1st scene of the app |  | Design 2nd scene of the app |  | Design 3rd scene of the app |  | Design 4th scene of the app
2016-11-22 | Design 1st scene of the app... |  | Design 2nd scene of the app... |  | Design 3rd scene of the app... |  | Design 4th scene of the app...
2016-11-23 | Design 1st scene of the app... |  | Design 2nd scene of the app... |  | Design 3rd scene of the app... |  | Design 4th scene of the app...
2016-11-24 | Design 1st scene of the app... |  | Design 2nd scene of the app... |  | Design 3rd scene of the app... |  | Design 4th scene of the app...
2016-11-25 | Design 1st scene of the app... |  | Design 2nd scene of the app... |  | Design 3rd scene of the app... |  | Design 4th scene of the app...
2016-11-26 | Design 1st scene of the app... |  | Design 2nd scene of the app... |  | Design 3rd scene of the app... |  | Design 4th scene of the app...
2016-11-27 | Externals exam
2016-11-28
2016-11-29
2016-11-30
2016-12-01
2016-12-02
2016-12-03
2016-12-04
2016-12-05
2016-12-06
2016-12-07
2016-12-08
2016-12-09
2016-12-10
2016-12-11
2016-12-12
2016-12-13
2016-12-14
2016-12-15
2016-12-16
2016-12-17
2016-12-18
2016-12-19
2016-12-20
2016-12-21
2016-12-22
2016-12-23
2016-12-24
2016-12-25
2016-12-26
2016-12-27
2016-12-28
2016-12-29
2016-12-30
2016-12-31
2017-01-01
2017-01-02
2017-01-03
2017-01-04
2017-01-05
2017-01-06
2017-01-07
2017-01-08
2017-01-09
2017-01-10
2017-01-11
2017-01-12
2017-01-13
2017-01-14
2017-01-15